## Product_Backlog
Product Backlog
Item Code Legends
| Project | PRJ
| Ad-Hoc | AH
| Others | O
Item # | Product Backlog | User Stories | Story Points (Size & Complexity) | Priority | Remarks | Status
PRJ-1 | Preliminary Setup | Requirement Review | 1
|  | Project Plan | 3 | 1
|  | CM Plan | 2
|  | Environment Setup and Deployment | 2
|  | Test Planning | 4
|  | Research And Study | 3
|  | Training and Presentation | 2 | 1
PRJ-2 | UI Mockup screen for Login page | UI Mockup | 5
|  | HL/Detail Design | 3
|  | Test Cases Preparation | 3 | 5
|  | System Testing | 3
|  | Research And Study | 3
|  | Training and Presentation | 2
PRJ-3 | Login Page | Coding | 5 | 1
|  | Smoke Testing | 1
|  | System Testing | 3
|  | QC Status Report | 1

## Sprint_Burndown_Chart
Burndown Chart
Sprint 1
|  |  |  | Project | Human Resources | Leaves | AF | Mon | Tue | Wed | Thu | Fri
AF-HRS Table: Assume we work 6 hrs per day. If otherwise, chance value in cell B9 |  |  |  | Project | DEV Engineer |  | 1 | 0.5 | 1 | 1 | 1 | 1
[5 empty] | DGN Engineer |  | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0.5
[5 empty] | QA Engineer |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
AF | Hrs |  |  |  | PM |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
1 | 6 |  |  |  | QM |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
0.9 | 5.4 |  |  |  | DM |  | 1 | 1 | 1 | 1 | 1 | 1
0.8 | 4.8 |  |  |  | EM |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
0.7 | 4.2
0.6 | 3.6
0.5 | 3
0.4 | 2.4
0.3 | 1.8
0.2 | 1.2
0.1 | 0.6
0 | 0
[7 empty] | SUM-AF | 2.9 | 2.9 | 3.4 | 3.4 | 3.4
[7 empty] | SUM-HRS | 17.4 | 17.4 | 20.4 | 20.4 | 20.4
[7 empty] | Total Hrs Available | 96
[7 empty] | Total Hrs Estimated | 35.5
[7 empty] | Total Story Points (Planned) | 15
[7 empty] | Total Story Points (Earned) | 0
(Remaining Effort - in Hrs)
[8 empty] | Mon | Tue | Wed | Thu | Fri
Item # | Product Backlog | User Stories | Story Points (Size & Complexity) | Tasks | Who | Status | Estimated Duration (Hrs) | 2012-07-30 | 2012-07-31 | 2012-08-01 | 2012-08-02 | 2012-08-03
PRJ-1 | Preliminary Setup | Requirement Review | 1 | Requirement Review | All | Ongoing | 16 | 8
|  | Project Plan | 3 | Project Plan - Preparation | PM | Not Started | 4 | 4
|  | Project Plan |  | Project Plan - Review |  |  | 1
|  | CM Plan | 2 | CM Plan - Preparation | PM | Not Started | 1 | 0.5
|  | CM Plan |  | CM Plan - Review |  |  | 0.5
|  | Environment Setup and Deployment | 2 | Environment Setup and Deployment - Rework After Review | QA Engineer | Not Started | 4 | 0.5
|  | Test Planning | 2 | Test Planning - Preparation | QA Engineer | Completed | 4 | 0
|  | Test Planning |  | Test Planning - Review |  |  | 1
|  | Research And Study | 3 | Research And Study - Review | DEV Engineer | Completed | 2 | 0
|  | Training and Presentation | 2 | Training and Presentation - Rework After Review | DEV Engineer | Not Started | 2 | 0.5
TOTAL |  |  | 15 |  |  |  | Day0 | Day1 | Day2 | Day3 | Day4 | Day5
[7 empty] | 35.5 | 13.5 | 0 | 0 | 0 | 0

## Legends
User Stories | Story Points | FTE | Hrs | Human Resources
Requirement Review | 1 | 1 | 6 | DEV Engineer
Project Plan | 3 | 0.9 | 5.4 | DGN Engineer
CM Plan | 2 | 0.8 | 4.8 | QA Engineer
Environment Setup and Deployment | 2 | 0.7 | 4.2 | PM
UI Mockup | 5 | 0.6 | 3.6 | QM
Test Planning | 2 | 0.5 | 3 | DM
HL/Detail Design | 3 | 0.4 | 2.4 | EM
Test Cases Preparation | 3 | 0.3 | 1.8 | DB Engineer
Test Data Preparation | 5 | 0.2 | 1.2
Coding | 5 | 0.1 | 0.6
Test Automation Scripts Preparation | 5 | 0 | 0
Test DB Scripts Preparation | 5
Smoke Testing | 1
System Testing | 3
Defective/New Issues Verification | 1
Regression Testing | 3
Automation Testing | 3
Performance Testing | 5
QC Status Report | 1
Documentation | 2
Research And Study | 3
Training and Presentation | 2
*Smoke Testing is taken as basis to give Story Point
Tasks
Requirement Analysis and Review
Project Plan - Preparation
Project Plan - Review
Project Plan - Rework After Review
CM Plan - Preparation
CM Plan - Review
CM Plan - Rework After Review
Environment Setup and Deployment
UI Mockup - Design
UI Mockup - Review
UI Mockup - Rework After Review
Test Planning - Preparation
Test Planning - Review
Test Planning - Rework After Review
HL/Detail Design - Preparation
HL/Detail Design - Review
HL/Detail Design - Rework After Review
Test Cases - Preparation
Test Cases - Review
Test Cases - Rework After Review
Test Data - Preparation
Test Data - Review
Test Data - Rework After Review
Coding
Coding - Review
Coding - Rework After Review
Test Automation Scripts - Preparation
Test Automation Scripts - Review
Test Automation Scripts - Rework After Review
Test DB Scripts - Preparation
Test DB Scripts - Review
Test DB Scripts - Rework After Review
Smoke Testing
System Testing
Regression Testing
Automation Testing
Performance Testing
QC Status Report
Documentation - Preparation
Documentation - Review
Documentation - Rework After Review
Research And Study
Training and Presentation